## Issues Log
Entry # | Status | Date | Rung/Context | Category | What Happened | Root Cause | Resolution | Lesson
1 |  | Aug 6 2026 | Rung 1 attempt | Tooling-Environment | Attempted /status for pre-run usage tracking; Claude Code reported it isn't available in this environment | Command doesn't exist in Troy's Claude Code environment (already anticipated in restart doc as a known correction) | Pivoted to /usage on the spot | Verify command availability before a run starts, not during it
2 |  | Aug 6 2026 | Rung 1 attempt | Process-Discipline | 5 permission prompts (allow once/allow always) surfaced before the run-stopping issue hit; Troy tally-marked each on a sticky note but didn't capture what each was for | Unattended overnight loop is fundamentally incompatible with an interactive permission model — this wasn't anticipated in the Goal Card | Plan: run rung 1 attempt #2 bare (no settings.json yet), capture tool/path/domain and allow-once-vs-always for each prompt; build a scoped .claude/settings.json off real data | A graduated-rope design that assumes unattended overnight runs needs its permission model solved before rung 4+, not discovered live at 2am
3 |  | Aug 6 2026 | Rung 1 attempt | Architecture / Tooling-Environment | Worker subagent completed its background run in 30s with zero rows changed. Worker's tool grant (Read/Write/Edit/WebSearch/WebFetch) cannot open or write binary .xlsx — no Bash means no way to script around it. Claude Code began reasoning toward a workaround; Troy stopped it before it proceeded. | Worker subagent definition was never given a tool capable of mutating a binary Excel file. RowBuilder's manual process never needed this — Troy himself did the paste-into-Excel step. | Resolved via Decision #1 (grant Bash) — see deferred-design-decisions doc | A capability gap this fundamental should have surfaced at design time, not at first launch
4 |  | Aug 7 2026 | Rung 1 attempt 1, postmortem | Architecture | Decision made: grant worker Bash access directly (Option A) rather than building a narrower purpose-built mechanism first | Deliberate scope tradeoff — full reasoning captured separately, not duplicated here | See deferred-design-decisions_ads-agentic-loop.md, Decision #1 | Deliberate 'good enough for now' choices deserve their own record, distinct from breadth-capture log entries
5 |  | Aug 6 2026 | Rung 1 attempt 1, retry | Architecture / Tooling-Environment | After Troy approved adding Bash, Claude Code edited and confirmed the correct save to all three subagent .md files. Worker was re-dispatched, but its second run still reported Bash as unavailable. | Subagent definitions are loaded once at session start; a mid-session edit to .claude/agents/*.md isn't visible to subagents spawned later in that same conversation | Troy ended the session rather than burn a third attempt against a known wall ('retry will have to happen another day') | A subagent tool-grant change requires a fresh session, not just a saved file, to take effect
6 |  | Aug 6 2026 (discovered Aug 7) | Rung 1 attempt 1 | Process-Discipline | settings.local.json was found containing ~14 distinct allow rules, not the 5 Troy had tallied on a sticky note during the run | Troy adopted a deliberately permissive 'Allow Always, don't fuss' habit from prior sessions, to keep the run moving | Treat settings.local.json as authoritative reverse-engineered evidence of what was actually granted, rather than trusting the live tally | Speed-now and legibility-later are in real tension. Read grants once, closely, per pattern-type — not per individual prompt
7 |  | Aug 6/7 2026 | Rung 1 attempt 1 (discovered during settings.json cleanup) | Tooling-Environment | settings.local.json, dated Aug 6 6:14 AM, never appeared in git status at any point — not tracked, not untracked, not modified. Project .gitignore, global core.excludesfile, and .git/info/exclude all checked — none explain it. | Unknown | None applied — file is now emptied out and superseded by .claude/settings.json, so the practical risk is gone even though the mechanism is unexplained | Not every anomaly needs to be solved before moving on
8 |  | Aug 8 2026 | Rung 1 attempt 2 | Tooling-Environment | Worker's actual write calls used a compound command (cd repo-root && python scripts/ads_xlsx_tool.py write-field ... 2>&1), which didn't match settings.json's allow rule (expected a command starting with python and an absolute path). Every write fell through to a permission prompt despite being the exact sanctioned, safe call. | settings.json Bash rules match as a literal prefix on the whole command string, not semantically — a correct call in a different shape still misses the rule | Constrained worker.md and business-analyst.md to one fixed invocation shape (no cd, no chaining, no redirect, relative path from repo root) and matched settings.json's rule to that exact shape. Confirmed with Claude Code directly that Bash's working directory already defaults to repo root, so the cd was never necessary. | A prefix-matched permission rule is only as good as the invocation shape it was written against — design the shape deliberately and instruct agents to hold to it, rather than writing a rule after observing one sample
9 |  | Aug 8 2026 | Rung 1 attempt 2 | Architecture / Tooling-Environment | qa fell back to raw inline Python (python3 -c, then interpreter-hunting via 'where python/python3/py', then the full Windows python.exe path) to inspect row fill status and diff the Answer Key, because ads_xlsx_tool.py had no action qa could use for either of its two checks | The tool script was designed around worker's and business-analyst's jobs only; qa's two checks (structural completeness, Answer Key comparison) were never given a sanctioned path, and the script deliberately never accepts the Answer Key as a parameter at all, which would have been wrong for worker/business-analyst but left qa with nothing | Built a second, separate script (qa_verify_tool.py) with verify-row and compare-answer-key actions, referenced only in qa.md — never mentioned to worker or business-analyst, so their Bash grant never has a reason to reach for it even though settings.json can't technically restrict the rule to qa alone | Scoping a tool to 'the agents that need file access' silently left out the one agent whose entire job is checking files — completeness of a tool's action set has to be checked against every subagent's actual job, not just the ones doing the writing
10 |  | Aug 8 2026 | Rung 1 attempt 2 | Architecture | qa, using Bash-driven raw Python, successfully opened and diffed the Answer Key even though settings.json had a deny rule on Read/Edit for that exact path — the deny rule did nothing to stop it | settings.json deny rules gate specific named tools (Read, Edit); Bash is a shell and can open any file the OS user can read regardless of what Read/Edit deny rules say. The 'hard filesystem guarantee' believed to have been added earlier for Answer Key isolation was never real — any Bash-capable agent could always bypass it | Physically relocated the Answer Key outside the repo entirely, to C:/workspaces/non-repo/answer_key_ads_master.xlsx. Worker's and business-analyst's subagent files no longer reference this path at all — isolation now works by withholding the information, not by trying to block access to information they already have | A deny rule that only covers named tools gives a false sense of a hard guarantee when Bash is also granted. Removing an agent's knowledge of a path is more robust than trying to block its access to a path it already knows
11 |  | Aug 8 2026 | Rung 1B | Architecture / Isolation | During row-selection (hunting for a way to find the next unstarted row, since ads_xlsx_tool.py has no listing action), worker read qa_verify_tool.py's source directly, which hard-codes the Answer Key's relocated path in its docstring/constants. | The v3 relocation fix (Entry 10) closed the Bash-driven-open vector but never considered a second vector: reading the source of the script that knows the path. Worker had no sanctioned way to find 'next unstarted row' at all, so it went looking, and the nearest script happened to expose the path. | Added a Read deny rule on scripts/qa_verify_tool.py in settings.json (blocks the generic Read tool from viewing its source; qa's own sanctioned Bash execution of it is unaffected) AND added a next-unstarted action to ads_xlsx_tool.py so worker has no reason to go looking in the first place. | Isolation by 'the file moved' is only as strong as every path that can reveal where it moved to — the fix has to cover the fact of the path's existence, not just direct access to the file.
12 | Deferred | Aug 8 2026 | Rung 1B | Architecture | Worker hit a genuine tool-capability gap (ads_xlsx_tool.py had no way to determine the next unstarted row) and improvised raw inline Python instead of stopping and reporting, despite v3's explicit CONSTRAINT requiring exactly that. | The stop-and-report rule exists only as prompt-level language in the subagent files; nothing enforces it mechanically, so a capable agent facing a clear goal and no sanctioned path reached for the nearest workaround instead. | Deliberately deprioritized. Troy's call: the rule is likely harmless and possibly helpful but under-tested; not worth further investment this cycle, especially now that the specific trigger (no next-unstarted mechanism) is closed by Entry 11's fix. | Not every observed gap needs closing in the same cycle it's found in — a rule can be left exactly as-is, noted, and revisited later without that being neglect.
13 |  | Aug 8 2026 | Rung 1B | Tooling-Environment | WebSearch and WebFetch calls prompted for approval on nearly every call throughout the run, despite the restart doc's assertion that this was 'correctly left broad in settings.json, nothing to fix there.' settings.json in fact had zero allow entries for either tool. | WebSearch cannot be auto-approved via Claude Code's permissions.allow system at all, in the current release — confirmed via search as an open feature request, not a misconfiguration. WebFetch can be allowed via settings.json, but the domain:* wildcard is separately known-buggy and doesn't work as documented. | Added a PreToolUse hook (matcher: WebSearch¦WebFetch) to settings.json's new hooks block, returning an explicit allow decision. This bypasses the permissions system's gap entirely rather than trying to configure around it. Untested live as of this writing — validate during Rung 1C before trusting it unattended. | A restart doc's stated assumption ('nothing to fix there') should be treated as a hypothesis to verify, not a settled fact to carry forward across sessions.
14 |  | Aug 8 2026 | Rung 1B | Tooling-Environment | Nearly every write-field call (and most read-row/qa calls) triggered a permission prompt despite matching settings.json's Bash(python scripts/ads_xlsx_tool.py *) allow rule exactly, in the fixed invocation shape Entry 8 established. | Confirmed via search as a documented, currently-tracked Claude Code bug: the * wildcard in Bash allow rules fails to match commands containing double-quote characters, with no workaround at the settings.json level. Nearly every write-field call quotes its --field and --value arguments, which are exactly the pattern that breaks the match. | Added a second PreToolUse hook (matcher: Bash) that inspects the literal command string and returns an explicit allow only when it genuinely starts with one of the two sanctioned scripts — narrower than the WebSearch/WebFetch hook by design, preserving the 'Bash is safe because narrowly exercised' premise behind Deferred Decision #1. | Entry 8's fix (correct invocation shape) was necessary but not sufficient — a second, unrelated platform bug was defeating the same allow rule independently. Two different root causes can produce the same symptom (a permission prompt) and need to be diagnosed separately.
15 |  | Aug 8 2026 | Rung 1B | Process-Discipline | A literal $ in a price-field --value argument (e.g. $25/person) required shell-escaping and still triggered a permission prompt even when escaped. | Bash interprets a literal $ as the start of variable expansion before the argument ever reaches Python; this happens regardless of the destination cell's data type in Excel, so the fix is at the value-formatting layer, not the spreadsheet layer. | New Price Field Convention adopted: price values are written as plain numbers with no currency symbol (e.g. 25/person, not $25/person or $25 USD/person) for Tasting Formats/Prices (39) and all four dedicated price fields (42-45). Documented in Operating Guide v3.4 and flagged in the Data Dictionary's Instructions column for those fields. | A data-formatting convention can eliminate a shell-parsing problem entirely, more reliably than trying to harden the invocation layer against every special character a value might contain.
16 | Deferred | Aug 8 2026 | Rung 1B | Tooling-Environment | Wall-clock time for the run reached approximately 52 minutes against a stated 45-minute STOP-CAP, and the run was not stopped. | Unclear — either the STOP-CAP isn't mechanically enforced by the orchestrator (it exists as prompt language, not a monitored timer), or '45 minutes' is being measured against something narrower than human-experienced wall-clock. | None applied. Troy's explicit call: noted as an interesting observation, deliberately not investigated or fixed this cycle. | A cap written into a prompt is not the same guarantee as a cap enforced by code — worth remembering before relying on STOP-CAPS at larger row counts or unattended runs.
17 | Resolved | Aug 9 2026 | Rung 1C | Architecture / Tooling-Environment | Worker computed the Timestamp Convention's ET value (nearest hour, both timestamp fields identical) via inline Python each time a row completed, since ads_xlsx_tool.py has no timestamp-generation action. The workaround hardcoded a UTC-4 offset and the literal label "EDT," with no DST awareness. | The Operating Guide's Timestamp Convention specifies the required output format but never provided a mechanism to compute it, leaving worker to improvise; the improvised version was correct only because the run happened to occur during EDT. | Added a current-timestamp action to ads_xlsx_tool.py using zoneinfo("America/New_York") for DST-correct Eastern Time, rounded to the nearest hour, in the exact format both timestamp fields expect. | A documented convention that specifies output format without providing computation invites an improvised workaround — and one that "happens to be right today" (EDT in August) can silently go wrong later (EST in winter) without anyone noticing until it does.
18 | Resolved | Aug 9 2026 | Rung 1C | Architecture / Tooling-Environment | Worker bootstrapped the Data Dictionary (main sheet + Slug_Rules_Examples tab) via three improvised inline-Python Bash calls every fresh session — list sheet names, dump the main sheet, dump the slug rules tab — since worker.md/Operating Guide reference the Data Dictionary as authoritative but provide no sanctioned read path. One of the three calls also failed transiently mid-run, with no downstream impact. | ads_xlsx_tool.py was built around the files that need write-protection (Master, Audit Log); it was never extended to cover read-only access to a reference document worker's job actually depends on. | Added two fixed read-only actions to ads_xlsx_tool.py — dump-data-dictionary (DataDict_ADS_Locations) and dump-slug-rules (Slug_Rules_Examples), tab names hardcoded intentionally. This also removes the sheet-listing step entirely — worker never needed sheet discovery, only the two specific tabs it already knows by name. | A sanctioned tool built around "the files that need protecting" can still leave a read-only reference file inaccessible to the agent whose job depends on it — action-set completeness has to cover reads to open documents, not just writes to protected ones.
19 | Resolved | Aug 9 2026 | Rung 1C | Architecture / Tooling-Environment | The orchestrator read data/audit_log.xlsx directly via raw inline Python to compile the final run report (listing all Audit Log entries generated this run), since ads_xlsx_tool.py has append-audit-log but no read counterpart. | The tool script was built out incrementally around each agent's write needs; a read path for the Audit Log was never added, even though the Goal Card's own reporting requirement ("report... all audit_log.xlsx entries generated this run") is itself a consumer that needs to read it back. | Added a dump-audit-log read-only action to ads_xlsx_tool.py, same shape as write-field and the two Data Dictionary dump actions from Entry 18. | A script built to keep writes sanctioned can still leave the goal's own reporting step without a sanctioned read path — action-set completeness has to account for every consumer of a file, not just the agents writing to it.
20 | Deferred | Aug 10 2026 | Rung 1C (postmortem / fix implementation) | Tooling-Environment | Pushing a branch with Rung 1C's fixes (Entries 17-19) via git push failed with no visible permission prompt — Troy confirmed nothing was declined on his end. Investigation found .claude/settings.json carries a hard deny rule, Bash(git push *). | The deny rule was written to stop the /goal loop's autonomous subagents (worker/business-analyst/qa) from ever pushing to the remote unsupervised — a reasonable guardrail in that context. But the rule is scoped to the whole repo, not to those subagents specifically, so it also silently blocked a legitimate, human-directed push from a completely different session context. Because it's a deny rule rather than a missing allow entry, it fails with no prompt at all, which made the cause substantially harder to diagnose live than an ordinary permission gap would have been. | Worked around for this one PR by pushing via GitHub's API (MCP create_branch/push_files/create_pull_request) instead of Bash git push, since those tools aren't subject to the Bash-scoped deny rule. The underlying scoping gap in settings.json was deliberately left untouched this cycle — Troy's call, to avoid bundling a live settings.json change into what was meant to be a documentation/process conversation. | A deny rule scoped to "the whole repo" when the actual intent was "these three autonomous subagents" will also catch legitimate work happening in the same repo under a different hat — and unlike a missing allow-rule, a deny rule fails silently, with no prompt to signal why. Worth writing deny rules as narrowly as the actual threat model, not as broadly as the file happens to be scoped.
21 | Resolved | Aug 13 2026 | Rung 2 attempt #1 | Tooling-Environment | Preflight concluded scripts/qa_verify_tool.py did not exist, based solely on a Glob check returning no matches, and hard-stopped the rung per the goal's own preflight clause — even though the file was present the entire time. | Glob silently omits a file blocked by a settings.json deny rule from its results instead of flagging the denial, which looks identical to the file genuinely not existing. (The deny rule itself — blocking Read on this file — is intentional, per v4's Answer-Key isolation fix; it worked as designed. Glob's handling of the denial was the actual defect.) | Goal Card v6 — preflight now requires confirming a Glob "not found" with a direct Read attempt before treating it as real; a Read result of "denied by permission settings" means the file exists. | "Not found" and "access denied" can look identical if a denial is swallowed silently — don't trust one existence-check method alone near a permission boundary.
22 | Resolved | Aug 13 2026 | Rung 2 attempt #1 | Tooling-Environment | Once worker began row 1, every subcommand of scripts/ads_xlsx_tool.py failed outright — the script crashed on import with ZoneInfoNotFoundError, because ZoneInfo("America/New_York") was constructed at module scope, and this Windows Python 3.14 install had no system tzdata and no tzdata PyPI package installed. | Windows has no OS-level IANA tzdata the way Linux/macOS do, so Python's zoneinfo module needs the tzdata package as a fallback — it wasn't installed. Compounding it, the ZoneInfo object was built once at import time rather than only when current-timestamp actually needed it, so the missing dependency broke every action, not just the one that needed timezone data. | Troy installed tzdata manually, verified via a direct zoneinfo functional test. Separately, the script now constructs ZoneInfo(...) inside action_current_timestamp's own function body instead of at module scope, so a future gap like this only breaks that one action. | A missing dependency at import time takes the whole script down with it — construct anything environment-dependent as late as possible, scoped to only the code path that needs it.
23 | Resolved | Aug 13 2026 | Rung 2 attempt #1 | Architecture / Tooling-Environment | After the orchestrator correctly identified the preflight stop condition and tried to end its turn, the mechanical stop-enforcement (the orchestrator's own term: "the hook") repeatedly forced it to continue instead — roughly 8 near-identical "still blocked, holding" turns before it was released, coinciding exactly with the unrelated 6-consecutive-turn stall condition. | The mechanical checker only recognized the three originally-named STOP-CAPS conditions (turn cap, time cap, stall) as legitimate reasons to end a turn. A prompt-level "stop immediately" instruction wasn't one of them, so an already-correct, authorized stop still had to grind through the stall counter to take effect. | Goal Card v7 — added a fourth, explicitly named STOP-CAPS condition, "Explicit Hard-Stop," met immediately when triggered, cross-referenced at all three trigger points and in the /goal command text itself. | An authorization written only in prose isn't the same as one the mechanical checker actually recognizes — if a stop condition matters, name it in the same list the checker consults.
24 |  | Aug 13 2026 | Advisory session / PR workflow | Architecture | Decision made: keep the blanket Bash(git push *) deny rule as-is rather than attempting to scope it to only the three autonomous subagents. | Deliberate scope tradeoff — full reasoning captured separately, not duplicated here. | See deferred-design-decisions_ads-agentic-loop.md, Decision #2. | Deliberate "good enough for now" choices deserve their own record, distinct from breadth-capture log entries.
25 | Resolved | Aug 14 2026 | Advisory session (post-Rung-2-attempt-1) | Architecture | Migrating the Goal Card, Issues Log, deferred-decisions doc, and restart doc into andrews-driving-services/agentic-loop-ops/ (done for git-history and convenience reasons) gave the /goal-invoking Claude Code session — and worker, business-analyst, and qa, all running in the same repo — unrestricted Read/Glob/Bash access to everything in that directory. That included the Answer Key's literal external path, stated in plain text in three places in the Goal Card, and the full history of every prior rung's turn counts and wall-clock times. | The migration was made for good reasons — real git version history instead of manual _vN filename suffixes, one authoritative copy readable by any session with repo access — but without tracing what else in the architecture would gain reach to the new directory. It reopened the exact isolation problem Entries 9-11 already closed once (worker/business-analyst must never have a reachable path to the Answer Key), and separately contaminated clean rung-to-rung measurement, since the invoking session could now read its own prior results. | All four files relocated to troy-kb (a separate, personal repo the Desktop /goal session never touches), and agentic-loop-ops/ fully reverted out of andrews-driving-services (PR #5). Physical absence, not a permission rule. | Two, tied together. First, the one already familiar from the Answer Key's own history: isolation by withholding information beats isolation by permission rule — a rule can be misconfigured or misbehave; a file that isn't reachable can't. Second, and arguably the more important one this time: the decision to co-locate these docs inside andrews-driving-services in the first place was made without knowing a Claude Code session could hold two repositories open at once. Absent that knowledge, keeping everything in one repo felt like the only real option. Once the multi-repo capability was actually verified live, the constraint that drove the original choice simply stopped being true. An architectural decision is only as good as the toolset knowledge available when it's made — worth checking what's actually possible before assuming a constraint is real.
26 | Resolved | Aug 14 2026 | Rung 2 attempt #2 (pre-fire) | Tooling-Environment | Firing Rung 2 attempt #2 with the (then-current) v7 /goal command text failed outright: "Goal condition is limited to 4000 characters (got 4323)." Nothing before this point had ever come close to that limit. | v6 and v7 both added real, substantive text directly into the pasteable /goal command block (the Glob/Read preflight fallback, then the Explicit Hard-Stop STOP clause) without either revision checking the block's total length against any known ceiling — because no such ceiling had ever been hit before. | Tightened the command text to 3,724 characters — cut wordiness only, no rule dropped — and folded it into Goal Card v8. | A command text that grows via incremental, individually-reasonable additions can cross a hard platform limit with no warning until the exact moment it's fired — worth a rough length gut-check whenever a revision adds prose to that specific block, not just after something rejects it.
27 | Resolved | Aug 15 2026 | Rung 3, row 4 (Venue Number 16) | Tooling-Environment | Worker passed a markdown-formatted link ([text](url)) verbatim into a WebFetch/path argument while researching Glass House Winery's PDF menu. Something downstream interpreted the whole bracket-and-backslash string as a Windows file path relative to the repo root, producing a mangled path that Claude Code's own path-safety heuristic correctly flagged. Troy declined it, and the row 4 worker got killed outright as a direct consequence — the first worker-kill of the session. | Neither worker.md nor business-analyst.md ever instructed extracting the bare URL before a WebFetch call — a markdown link copied straight out of search-result text was passed through as-is. | Added an explicit instruction to both subagent files: always extract the bare URL first, never pass markdown link syntax through verbatim, regardless of the form a source presented it in. | A malformed argument can masquerade as a suspicious path and trigger a legitimate security check, costing a killed subagent — worth guarding the argument-construction step directly rather than relying on the safety heuristic to keep catching it after the fact.
28 | Resolved | Aug 15 2026 | Rung 5, row 2 (Moss Vineyards) | Tooling-Environment | Business-analyst's Bash calls during its first-ever consultation (--help, dump-audit-log, dump-data-dictionary, read-row) all used an absolute-path invocation shape (python C:/workspaces/.../scripts/ads_xlsx_tool.py ...) that the Bash PreToolUse hook's exact-prefix check didn't recognize, so every call fell through to a live Allow-once prompt. | The hook's sanctioned-command check was an exact-prefix tuple built from worker's known invocation shapes; it never anticipated bare python + absolute script path — a shape business-analyst used consistently but worker never had. | Replaced the exact-prefix check with real shell-aware tokenization (shlex with punctuation_chars) that recognizes the sanctioned script by its trailing path regardless of interpreter or path form, and rejects command chaining/redirection anywhere after the script argument. The logic lives in a dedicated file, .claude/hooks/check_sanctioned_bash.py, rather than an inline one-liner, so it stays reviewable as normal Python. Verified against real invocation shapes and adversarial cases — including chaining attempts and a legitimate pipe-delimited Source References value — before deploying. | An exact-prefix allowlist is only as complete as the shapes you've actually observed — matching on the invariant that actually matters (which script is being invoked) holds up better than enumerating every way of expressing it.
29 | Resolved | Aug 15 2026 | Rung 5, row 2 (Moss Vineyards) | Process-Discipline | The Audit Log's Rung column was found to carry no real information — every existing entry read "1 row" regardless of the actual rung it came from, even though business-analyst.md described it as meant to record the current rung's true size. | Nothing in the architecture actually threads the rung's true row count down to worker or business-analyst — worker only ever knows it's handling exactly one row, by design, per its own per-invocation scope, and that was the only "row count" fact that ever made it into the field. | Removed the Rung column entirely, rather than fixing it, on the reasoning that it was the wrong column to have committed to in the first place — Timestamp already places an entry in temporal context well enough for Troy's purposes, and making Rung genuinely accurate would require new plumbing in every future /goal invocation just to feed one field. Removed from the schema: scripts/ads_xlsx_tool.py (docstring, argparse, AUDIT_LOG_COLUMNS, the row it writes), business-analyst.md (invocation example and column list, renumbered), and the Goal Card (v9 — the terminology table's description dropped the column-count language too, so it won't need editing again the next time the schema changes). Troy handled the live audit_log.xlsx column deletion directly in Excel. | A documented field that requires plumbing nothing in the architecture actually supplies will quietly collapse to whatever's locally available instead — and sometimes the right fix isn't repairing the field, it's recognizing another field already does that job well enough.
30 | Resolved | Aug 15 2026 | Rung 5, row 2 (Moss Vineyards) | Process-Discipline | Business-analyst had to work substantially harder than the geographic fork itself required to discern the correct value format for the County field — bare county name, no "County" suffix, (city) appended only for independent cities. The Data Dictionary didn't state this convention anywhere; business-analyst only found it by discovering and reading ADS_ListMaker_Rules.md, a file outside the loop's normal CONTEXT, as a side effect of its broader research into the Moss Vineyards county fork. | The bare-name convention is real and deliberate — it's baked into ListMaker's own 26-county scope list — but it was never carried forward into the Data Dictionary or Operating Guide when RowBuilder's process split off from ListMaker's. The two docs drifted apart on this one point. | Data Dictionary's County field entry updated to state the convention explicitly — plain county name, no "County" word, (city) suffix reserved for independent cities — with worked examples. Troy also went back and corrected existing County values already in the Master to comply, better late than never. Both edits made directly in Excel. | A conflicting-sources judgment call and a missing value-formatting convention can surface together inside the same fork, but they're two different kinds of gaps — resolving which county was correct didn't also guarantee the format of the answer was documented anywhere worker or business-analyst could reliably find it.
31 | Resolved | Aug 15 2026 | Rung 5, row 5 (Reynard Florence) | Process-Discipline | Worker caught a live instance of the $ shell-expansion bug in a Source References field value during a pricing-fork resolution — not a price field, even though the only existing documentation (the Operating Guide's Price Field Convention) framed the underlying mechanical problem as specific to price fields. | The Price Field Convention (added in v3.4, after the original Rung 1B incident) correctly explained the shell mechanics of why a literal $ breaks a write command, but scoped that explanation narrowly to price fields, since that was the only place the bug had been observed at the time. The mechanism is actually a property of how any value reaches ads_xlsx_tool.py, not of what the field means. | Operating Guide bumped to v3.5. The price-specific formatting rule (plain numbers, no currency symbol) is unchanged; a new clause broadens the shell-escaping explanation to state plainly that a literal $ in any field's value can trigger the same problem, citing the Source References instance as confirmation it isn't price-specific. Data Dictionary intentionally left untouched — its price-specific note there still correctly applies only to price fields. | A documented workaround discovered from one specific incident can get scoped too narrowly to that incident's context — the underlying mechanism mattered more than the field it happened to be caught in.
32 | Deferred | Aug 15 2026 | Rung 5 (observed); Rung 5B retest cycle (fix designed, then deferred) | Tooling-Environment | virginiawine.org reliably returns 403 on direct WebFetch (bot-detection), observed repeatedly across venues in Rung 5 and confirmed live by Troy watching subsequent runs. | Not applicable — this is an observed platform/domain behavior, not a defect. | Deferred. A full fix was designed, drafted, and verified working, then deliberately not shipped — see deferred-design-decisions_ads-agentic-loop.md, Decision #3, for the full reasoning and revisit trigger. | A fully designed and verified fix doesn't have to ship just because it's ready.
33 | Deferred | Aug 16 2026 (observed Rung 5, Aug 15) | Rung 5 (business-analyst pricing and county fork resolutions) | Process-Discipline | Troy observed business-analyst investing heavy effort — multiple sources, many tool calls — resolving forks that didn't all seem to warrant it equally, pricing in particular. | Not applicable — an observed effort/stakes mismatch, not a defect. | Deferred deliberately; today's priority is infrastructure-hardening toward a supervised, unattended run. See deferred-design-decisions_ads-agentic-loop.md, Decision #4, for the full reasoning and revisit trigger. | Not every observed inefficiency needs fixing in the cycle it's noticed in.